## Sheet1
SEQUENCING JOBS
STRATEGY | JOB | START DAY | DUE DATE | DURATION (DAYS) | FLOW TIME | COMPLETION DATE | JOB LATENESS
FCFS | A | 275 | 313 | 8 | 8 | 283 | 0
A-B-C-D-E | B | 275 | 312 | 16 | 24 | 299 | 0
| C | 275 | 325 | 40 | 64 | 339 | 14
| D | 275 | 314 | 5 | 69 | 344 | 30
| E | 275 | 314 | 3 | 72 | 347 | 33
| TOTAL |  |  | 72 | 237 | 1612 | 77
SUMMARY OF SEQUENCING JOBS
STRATEGY | JOB | START DAY | DUE DATE | DURATION (DAYS) | FLOW TIME | COMPLETION DATE | JOB LATENESS | RULE | AVERAGE COMPLETION TIME | UTILIZATION METRICS | AVERAGE NUMBER OF JOBS | AVERAGE LATENESS
SPT | B | 275 | 312 | 16 | 16 | 291 | 0
B–D–A–C–E | D | 275 | 314 | 5 | 21 | 296 | 0 | FCFS | 47.4 | 0.3038 | 3.2917 | 15.4
| A | 275 | 313 | 8 | 29 | 304 | 0 | SPT | 41.4 | 0.34783 | 2.875 | 10.4
| C | 275 | 325 | 40 | 69 | 344 | 19 | EDD | 42 | 0.34286 | 2.9167 | 10.4
| E | 275 | 314 | 3 | 72 | 347 | 33 | LPT | 61.2 | 0.23529 | 4.25 | 9.4
| TOTAL |  |  | 72 | 207 | 1582 | 52
NB: SPT IS THE BEST CHOICE FOR STRATEGY
STRATEGY | JOB | START DAY | DUE DATE | DURATION (DAYS) | FLOW TIME | COMPLETION DATE | JOB LATENESS
EDD | B | 275 | 312 | 16 | 16 | 291 | 0
B–A–D–C–E | A | 275 | 313 | 8 | 24 | 299 | 0
| D | 275 | 314 | 5 | 29 | 304 | 0
| C | 275 | 325 | 40 | 69 | 344 | 19
| E | 275 | 314 | 3 | 72 | 347 | 33
| TOTAL |  |  | 72 | 210 | 1585 | 52
STRATEGY | JOB | START DAY | DUE DATE | DURATION (DAYS) | FLOW TIME | COMPLETION DATE | JOB LATENESS
LPT | E | 275 | 314 | 3 | 3 | 278 | 0
E–C–A–D–B. | C | 275 | 325 | 40 | 43 | 318 | 0
| A | 275 | 313 | 8 | 51 | 326 | 13
| D | 275 | 314 | 5 | 56 | 331 | 17
| B | 275 | 312 | 16 | 153 | 1253 | 17
| TOTAL |  |  | 72 | 306 | 2506 | 47